## README
Disclosures: Rural Health Transformation Program Reporting (CMS-10949; OMB 0938-TBD) This is a new collection of information request that has not been approved by the Office of Management and Budget (OMB). At this time the OMB control number has yet to be determined. OMB will issue the control number upon their approval of the 30-day collection of information request. • This is a draft document that is subject to change. • The draft template is not approved by OMB. • Interested parties should refer to the Federal Register for dates/instructions on submitting comments specific to the draft template or any of parts of this collection of information request. • CMS is in the process of obtaining OMB’s approval of the template under the Paperwork Reduction Act (PRA) process. • CMS will inform when the final template has been approved by OMB. • Respondents should not complete/submit the draft template to CMS. • CMS will not accept the draft template.
RHT Program Project Plan Template
The purpose of this workbook is to provide States with an optional template to create their initiative project plans. States who wish to report their project plan information using this template should create a new project plan tab for each initiative. Each initiative milestone from the State application should be present in the initiative project plan. If the State would like to include additional tasks for a milestone, they may be reported as rows below the respective milestone. CMS will provide the list of milestones identified from the State application along with additional milestone guidance.
Idaho RHTP Project Plan Note:
Relationship to Idaho’s Approved Application: The milestone rows included in each initiative project plan correspond to the key activities and milestones established by stage and year in Idaho’s CMS-approved RHTP application and project narrative. The supporting task rows were developed by Idaho RHTP to operationalize, sequence, and track progress toward those approved milestones. The approved milestone language has been retained without modification.

## Initiative 1 Project Plan
Initiative 1: Improving Rural Access to Care Through Technology |  | Key |  | Status Report
As of July 31, 2026 |  | Stage |  | 4 | Complete
Designated State Lead: | Holly Walund | Milestone |  | 8 | In Progress - On Track
Team Members: | Liz Perkins, Cecilia Arritola, Adam McFarland, Robert Graff | Task |  | 0 | In Progress - Behind Schedule
|  |  |  | 3 | Not Yet Started
|  |  |  | 57 | Upcoming
Note: All milestones from the approved State application for this initiative are included in this project plan.
Number | Milestones/Tasks | Target Start | Target Due Date | Status | Task Owner | Notes
Stage 0 | Initiation and Procurement Phase
0.1 | Execute contracts and formalize partnerships | 2026-05-01 | 2026-10-12 | In Progress - On Track | RHTP team | Although Idaho’s initial implementation timeline was compressed because legislative spending authority did not become effective until April 10, 2026, the State accelerated procurement, solicitation, agreement, and partner-engagement activities following receipt of that authority and the onboarding of dedicated RHTP staff. These activities are proceeding in rolling waves, with early opportunities advancing while subsequent packages and agreements are finalized concurrently. Idaho has also maintained broader stakeholder engagement through recurring lobbyist and stakeholder calls, participation in the rural health conference, and related outreach activities. As of July 31, 2026, Idaho remained on track to complete the necessary awards and agreements in time to meet the October 30, 2026 obligation milestone.
0.1.1 | Establish procurement pathways and initial implementation approach | 2026-05-01 | 2026-10-12 | Complete | RHTP team | Establishes compliant state procurement specifications, RFP frameworks, and subgrant evaluation rubrics across core regional health system, technology, and clinical partner solicitations under SB 1453 authority.
0.1.2 | Develop and advance initial solicitation and agreement packages | 2026-05-01 | 2026-10-12 | Complete | RHTP and grants/contracts teams | Publishes formal solicitations to the state bidding portal, initiates public vendor inquiry windows, and manages partner application intake to ensure competitive open market engagement.
0.1.3 | Conduct evaluations, selections, and award development for initial opportunities | 2026-05-01 | 2026-10-12 | Complete | RHTP and grants/contracts teams | Convenes technical evaluation committees to score applicant qualifications, clinical delivery capabilities, budget alignment, and rural network coverage against established state guidelines
0.1.4 | Finalize subsequent procurement packages and execute remaining agreements | 2026-05-01 | 2026-10-12 | In Progress - On Track | RHTP and grants/contracts teams | Finalizes subaward negotiations, executes binding inter-agency/vendor contracts, and formally obligates Year 1 federal grant funds prior to the mandatory October 31, 2026 operational cutoff
0.2 | Conduct statewide technology readiness and facility assessments | 2026-11-01 | 2027-10-30 | In Progress - On Track | Pending vendor award | The RFP opened on July 10, 2026, and remained active as of the July 31 reporting date. The solicitation closed on August 21, 2026. IDHW is proceeding with evaluation and selection activities and anticipates completing the award and agreement-execution process by October 30, 2026.
0.2.1 | Finalize the assessment framework and participating-facility approach | 2026-11-01 | 2027-03-30 | In Progress - On Track | RHTP team / selected assessment vendor | Planned task supporting the approved milestone.
0.2.2 | Conduct assessments and document priority technology gaps | 2027-04-01 | 2027-10-30 | In Progress - On Track | Selected assessment vendor | Planned task supporting the approved milestone.
0.3 | Begin development of shared infrastructure strategy and interoperability based on CMS Interoperability Framework | 2026-07-01 | 2026-12-31 | Not Yet Started | RHTP team / State technology partners | State determined that provider education on CMS Interoperability Framework to be integrated into executed provider agreements tied to technology-related subawards. State RHTP team to develop and provide CMS Interoperability Framework supporting materials in Year 2. State agency leadership have participated in conversations with the Idaho Hospital Association and rural Critical Access Hospitals regarding interoperability and shared infrastructure for Electronic Health Records and how best to approach given current use of multiple different systems with different contract terms and timelines. It is anticipated that this effort will develop further in Year 2.
0.3.1 | Confirm governance, State lead, and facility participation requirements | 2026-07-01 | 2026-12-31 | Not Yet Started | RHTP team / State technology partners | Planned task supporting the approved milestone.
0.3.2 | Develop shared-infrastructure and interoperability roadmap | 2026-07-01 | 2026-12-31 | Not Yet Started | RHTP team / implementation partners | Planned task supporting the approved milestone.
0.4 | Initiate cybersecurity baseline assessments | 2026-07-01 | 2026-12-31 | In Progress - On Track | Pending vendor award | Cybersecurity Assessment Agreement executed and formal kick-off forthcoming
0.4.1 | Finalize cybersecurity assessment procurement and execute aggreement | 2026-07-01 | 2026-12-31 | Complete | RHTP team | Planned task supporting the approved milestone.
0.4.2 | Host vendor kick-off and begin contracted work | 2026-11-01 | 2026-12-31 | In Progress - On Track | ID RHTP Team / Selected cybersecurity vendor | Planned task supporting the approved milestone.
0.4.2 | Complete baseline assessments and summarize common gaps | 2027-01-01 | 2027-10-30 | In Progress - On Track | Selected cybersecurity vendor | Planned task supporting the approved milestone.
Stage 1 | Initial Implementation Phase
1.1 | Launch telehealth infrastructure enhancements (equipment, software) | 2027-01-01 | 2027-06-30 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
1.1.1 | Approve site-specific telehealth implementation plans | 2027-01-01 | 2027-06-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.1.2 | Install, configure, and validate telehealth equipment and software | 2027-01-01 | 2027-06-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.2 | Begin digital health and mobile app procurement | 2027-01-01 | 2027-06-30 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
1.2.1 | Define functional, security, and accessibility requirements | 2027-01-01 | 2027-06-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.2.2 | Procure and begin deployment of approved digital health tools | 2027-01-01 | 2027-06-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.3 | Implement cybersecurity upgrades | 2027-01-01 | 2027-09-30 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
1.3.1 | Prioritize remediation projects using baseline findings | 2027-01-01 | 2027-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.3.2 | Implement and validate cybersecurity improvements | 2027-01-01 | 2027-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.4 | Begin Idaho Health Alert Network (HAN) system modernization | 2027-01-01 | 2027-09-30 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
1.4.1 | Confirm modernization requirements and implementation sequence | 2027-01-01 | 2027-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.4.2 | Complete initial HAN modernization work and testing | 2027-01-01 | 2027-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.5 | Initiate training programs for providers and IT staff | 2027-04-01 | 2027-12-31 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
1.5.1 | Develop role-specific training materials and delivery schedule | 2027-04-01 | 2027-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.5.2 | Deliver initial training and document participation | 2027-04-01 | 2027-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
Stage 2 | Expansion and Integration Phase
2.1 | Establish regional telehealth networks and implement telepharmacy models | 2028-01-01 | 2028-06-30 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
2.1.1 | Formalize regional participation and operating arrangements | 2028-01-01 | 2028-06-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
2.1.2 | Launch telehealth and telepharmacy services in participating sites | 2028-01-01 | 2028-06-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
2.2 | Begin health management software rollout | 2028-01-01 | 2028-09-30 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
2.2.1 | Complete site readiness and configuration planning | 2028-01-01 | 2028-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
2.2.2 | Deploy software and support initial adoption | 2028-01-01 | 2028-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
2.3 | Deploy AI tools for revenue and care optimization | 2028-04-01 | 2028-09-30 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
2.3.1 | Review proposed tools for allowability, privacy, and security | 2028-04-01 | 2028-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
2.3.2 | Pilot approved tools and document early results | 2028-04-01 | 2028-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
2.4 | Launch emergency communication system upgrades (NG911) | 2028-04-01 | 2028-12-31 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
2.4.1 | Finalize upgrade designs and participating locations | 2028-04-01 | 2028-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
2.4.2 | Launch upgrades and complete initial operational testing | 2028-04-01 | 2028-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
Stage 3 | Evaluation and Refinement Phase
3.1 | Evaluate early outcomes of telehealth and digital health tools | 2029-01-01 | 2029-06-30 | Upcoming | Evaluation vendor / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
3.1.1 | Analyze adoption, access, and utilization data | 2029-01-01 | 2029-06-30 | Upcoming | Evaluation vendor / RHTP team | Planned task supporting the approved milestone.
3.1.2 | Complete midpoint findings and recommendations | 2029-01-01 | 2029-06-30 | Upcoming | Evaluation vendor / RHTP team | Planned task supporting the approved milestone.
3.2 | Enhance EHR upgrades and interoperability efforts | 2029-01-01 | 2029-09-30 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
3.2.1 | Assess implementation experience and remaining interoperability gaps | 2029-01-01 | 2029-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
3.2.2 | Implement prioritized EHR and interoperability enhancements | 2029-01-01 | 2029-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
3.3 | Scale health management data analytics | 2029-04-01 | 2029-12-31 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
3.3.1 | Validate common measures and data-sharing processes | 2029-04-01 | 2029-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
3.3.2 | Expand analytics dashboards across participating facilities | 2029-04-01 | 2029-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
3.4 | Continue cybersecurity monitoring and training | 2029-01-01 | 2029-12-31 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
3.4.1 | Monitor risks and remediation progress | 2029-01-01 | 2029-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
3.4.2 | Deliver refresher training and targeted technical assistance | 2029-01-01 | 2029-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
Stage 4 | Sustainability Preparation Phase
4.1 | Continue implementation of all tech solutions and data tools | 2030-01-01 | 2030-09-30 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
4.1.1 | Complete remaining implementation activities | 2030-01-01 | 2030-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
4.1.2 | Verify adoption across targeted rural facilities | 2030-01-01 | 2030-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
4.2 | Conduct usability assessments and adapt tools for local needs | 2030-01-01 | 2030-09-30 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
4.2.1 | Gather structured user and facility feedback | 2030-01-01 | 2030-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
4.2.2 | Implement approved usability and workflow improvements | 2030-01-01 | 2030-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
4.3 | Develop sustainability and maintenance models for infrastructure | 2030-04-01 | 2030-12-31 | Upcoming | RHTP team / participating facilities | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
4.3.1 | Estimate ongoing operating and maintenance requirements | 2030-04-01 | 2030-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
4.3.2 | Complete facility-level sustainability and maintenance plans | 2030-04-01 | 2030-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
Stage 5 | Closeout and Transition Phase
5.1 | Conduct final program evaluation and reporting | 2031-01-01 | 2031-12-31 | Upcoming | Evaluation vendor / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
5.1.1 | Compile final performance and expenditure information | 2031-01-01 | 2031-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
5.1.2 | Complete final evaluation and reporting | 2031-01-01 | 2031-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
5.2 | Assess outcomes in care access, efficiency, cost, and quality | 2031-01-01 | 2031-06-30 | Upcoming | Evaluation vendor / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
5.2.1 | Analyze outcome measures and implementation experience | 2031-01-01 | 2031-06-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
5.2.2 | Document conclusions, limitations, and lessons learned | 2031-01-01 | 2031-06-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
5.3 | Disseminate findings and ensure sustainable post-grant transitions | 2031-04-01 | 2031-12-31 | Upcoming | RHTP team / participating facilities | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
5.3.1 | Share results with stakeholders and State leaders | 2031-04-01 | 2031-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
5.3.2 | Transition supported systems to long-term owners | 2031-04-01 | 2031-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.

## Initiative 2 Project Plan
Initiative 2: Ensuring Accessible Quality Care Through Innovative Models |  | Key |  | Status Report
As of July 31, 2026 |  | Stage |  | 3 | Complete
Designated State Lead: | Holly Walund | Milestone |  | 6 | In Progress - On Track
Team Members: | Liz Perkins, Cecilia Arritola, Adam McFarland, Robert Graff | Task |  | 0 | In Progress - Behind Schedule
|  |  |  | 0 | Not Yet Started
|  |  |  | 53 | Upcoming
Note: All milestones from the approved State application for this initiative are included in this project plan.
Number | Milestones/Tasks | Target Start | Target Due Date | Status | Task Owner | Notes
Stage 0 | Initiation and Procurement Phase
0.1 | Execute contracts and engage partners | 2026-05-01 | 2026-10-30 | In Progress - On Track | RHTP team | Although Idaho’s initial implementation timeline was compressed because legislative spending authority did not become effective until April 10, 2026, the State accelerated procurement, solicitation, agreement, and partner-engagement activities following receipt of that authority and the onboarding of dedicated RHTP staff. These activities are proceeding in rolling waves, with early opportunities advancing while subsequent packages and agreements are finalized concurrently. Idaho has also maintained broader stakeholder engagement through recurring lobbyist and stakeholder calls, participation in the rural health conference, and related outreach activities. As of July 31, 2026, Idaho remained on track to complete the necessary awards and agreements in time to meet the October 30, 2026 obligation milestone.
0.1.1 | Confirm procurement and partnership pathways for Initiative 2 activities | 2026-05-01 | 2026-06-30 | Complete | RHTP team | Planned task supporting the approved milestone.
0.1.2 | Conduct initial engagement with state and program partners to refine implementation requirements | 2026-05-01 | 2026-07-31 | Complete | RHTP team / Partner Agency | Planned task supporting the approved milestone.
0.1.3 | Develop and complete internal review of initial solicitation and agreement packages | 2026-05-01 | 2026-10-12 | Complete | RHTP team | Planned task supporting the approved milestone.
0.1.4 | Publish, evaluate and award initiative 2 related procurements. | 2026-05-01 | 2026-10-12 | In Progress - On Track | RHTP / Partner Agency / IDHW Contracts and Procurements Services (CAPS) | Planned task supporting the approved milestone.
0.2 | Begin community needs assessments | 2026-11-01 | 2026-12-31 | In Progress - On Track | Implementation partner/ selected vendor | Community needs assessment activities will begin immediately following execution of the applicable contract or agreement, anticipated no later than October 31, 2026. The selected partner will initiate assessment planning and data collection upon authorization to proceed, consistent with the approved project narrative’s 2026 implementation timeline.
0.2.1 | Finalize the community needs assessment methodology, data sources, and engagement plan | 2026-10-13 | 2026-10-31 | In Progress - On Track | Implementing partners / RHTP team | Planned task supporting the approved milestone.
0.2.2 | Initiate data collection and engagement with participating rural communities and healthcare partners | 2026-11-01 | 2026-11-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
0.3 | Plan deployment of diagnostic kiosks, telehealth pods, and pharmacy access points | 2026-11-01 | 2027-03-31 | Upcoming | Implementation partner/ selected vendor | Implementation of this milestone is dependent on execution of the applicable contract or award. As of July 31, 2026, Idaho was actively procuring the services and implementation partners necessary to begin this work. Deployment planning will begin following completion of the applicable procurement and agreement activities, anticipated immediately after the October 31, 2026 obligation milestone.
0.3.1 | Conduct implementation kickoff and confirm partner roles, deliverables, and deployment requirements | 2026-11-01 | 2026-11-15 | In Progress - On Track | Implementing partners / RHTP team | Planned task supporting the approved milestone.
0.3.2 | Finalize site-selection and readiness criteria | 2026-11-01 | 2026-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
0.3.3 | Engage eligible rural sites and assess deployment readiness | 2026-12-01 | 2027-02-28 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
0.3.4 | Select initial locations and complete site-specific deployment plans | 2027-01-01 | 2027-03-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
0.4 | Development of curriculum for health extender certification programs | 2026-11-01 | 2027-03-31 | In Progress - On Track | State partner / RHTP team | Idaho RHTP is coordinating with the Idaho Military Division and other state partners to define partnership roles, identify existing EMS health extender training resources that may be leveraged, and refine program and curriculum requirements. The Idaho RHTP team and Military Division have been working during July and August 2026 on the development of a MOA to formalize the partnership and implementation approach. The current available version is not yet executed but is anticipated to be finalized in early September 2026. Curriculum development and refinement will continue as partner roles and applicable agreements are finalized.
0.4.1 | Review existing competencies, training resources, and applicable certification requirements | 2026-11-15 | 2027-01-15 | Upcoming | State partner / RHTP team | Planned task supporting the approved milestone.
0.4.2 | Develop the draft health-extender curriculum and certification framework | 2027-01-01 | 338613 | Upcoming | State partner / training partners | Planned task supporting the approved milestone.
0.4.3 | Complete partner review and finalize the curriculum, training plan, and certification process | 2027-02-01 | 2027-03-31 | Upcoming | State partner / training partners | Planned task supporting the approved milestone.
Stage 1 | Initial Implementation Phase
1.1 | Begin installation of diagnostic and telehealth infrastructure in community locations | 2027-01-01 | 2027-06-30 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
1.1.1 | Complete site agreements and installation planning | 2027-01-01 | 2027-06-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.1.2 | Install and validate diagnostic kiosks and telehealth pods | 2027-01-01 | 2027-06-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.2 | EMS workgroup convened | 2027-01-01 | 2027-03-31 | Upcoming | RHTP team / EMS partners | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
1.2.1 | Confirm membership, charter, and priority work products | 2027-01-01 | 2027-03-31 | Upcoming | RHTP team / EMS partners | Planned task supporting the approved milestone.
1.2.2 | Convene workgroup and establish action plan | 2027-01-01 | 2027-03-31 | Upcoming | RHTP team / EMS partners | Planned task supporting the approved milestone.
1.3 | Remote patient monitoring and pharmacy access solutions initiated | 2027-01-01 | 2027-09-30 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
1.3.1 | Finalize implementation models and participating sites | 2027-01-01 | 2027-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.3.2 | Launch initial remote monitoring and pharmacy access services | 2027-01-01 | 2027-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.4 | Hiring and training initial cohort of health extenders in rural communities | 2027-01-01 | 2027-09-30 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
1.4.1 | Recruit and select initial health extender cohort | 2027-01-01 | 2027-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.4.2 | Complete training and deploy participants in rural communities | 2027-01-01 | 2027-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
Stage 2 | Expansion and Integration Phase
2.1 | Enhance remote patient monitoring and pharmacy access solutions | 2028-01-01 | 2028-09-30 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
2.1.1 | Review early utilization and implementation feedback | 2028-01-01 | 2028-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
2.1.2 | Expand and refine supported services | 2028-01-01 | 2028-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
2.2 | Continue health extender recruitment and integration with healthcare partners | 2028-01-01 | 2028-12-31 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
2.2.1 | Recruit and train additional participants | 2028-01-01 | 2028-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
2.2.2 | Strengthen supervision, referral, and integration processes | 2028-01-01 | 2028-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
2.3 | Begin building shared infrastructure (e.g., credentialing, prior authorization systems) | 2028-01-01 | 2028-12-31 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
2.3.1 | Document common administrative barriers and requirements | 2028-01-01 | 2028-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
2.3.2 | Develop draft shared-infrastructure models | 2028-01-01 | 2028-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
Stage 3 | Evaluation and Refinement Phase
3.1 | Continue training and deploying health extenders in rural areas | 2029-01-01 | 2029-12-31 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
3.1.1 | Deliver ongoing training and technical assistance | 2029-01-01 | 2029-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
3.1.2 | Monitor placement, integration, and retention | 2029-01-01 | 2029-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
3.2 | Continue evaluation of diagnostic and community care models | 2029-01-01 | 2029-12-31 | Upcoming | Evaluation vendor / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
3.2.1 | Conduct stakeholder feedback sessions | 2029-01-01 | 2029-12-31 | Upcoming | Evaluation vendor / RHTP team | Planned task supporting the approved milestone.
3.2.2 | Complete midpoint evaluation and recommendations | 2029-01-01 | 2029-12-31 | Upcoming | Evaluation vendor / RHTP team | Planned task supporting the approved milestone.
Stage 4 | Sustainability Preparation Phase
4.1 | Enhance cross-training of health extenders | 2030-01-01 | 2030-06-30 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
4.1.1 | Identify priority cross-training needs | 2030-01-01 | 2030-06-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
4.1.2 | Deliver expanded training and document completion | 2030-01-01 | 2030-06-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
4.2 | Support sustained integration of health extenders and remote care systems | 2030-01-01 | 2030-12-31 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
4.2.1 | Assess organizational and financing requirements | 2030-01-01 | 2030-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
4.2.2 | Implement integration and transition plans | 2030-01-01 | 2030-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
4.3 | Finalize EMS coverage maps and health extender optimization strategies | 2030-01-01 | 2030-12-31 | Upcoming | RHTP team / EMS partners | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
4.3.1 | Validate coverage and workforce data | 2030-01-01 | 2030-12-31 | Upcoming | RHTP team / EMS partners | Planned task supporting the approved milestone.
4.3.2 | Complete optimization recommendations and shared-resource agreements | 2030-01-01 | 2030-12-31 | Upcoming | RHTP team / EMS partners | Planned task supporting the approved milestone.
Stage 5 | Closeout and Transition Phase
5.1 | Conduct final evaluation of initiative outcomes | 2031-01-01 | 2031-12-31 | Upcoming | Evaluation vendor / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
5.1.1 | Complete final data analysis | 2031-01-01 | 2031-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
5.1.2 | Document outcomes, lessons learned, and recommendations | 2031-01-01 | 2031-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
5.2 | Complete reporting on health access improvements, workforce impacts, and care quality | 2031-01-01 | 2031-12-31 | Upcoming | Evaluation vendor / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
5.2.1 | Compile final narrative and metric reporting | 2031-01-01 | 2031-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
5.2.2 | Submit required final reports | 2031-01-01 | 2031-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
5.3 | Transition successful models to long-term funding and oversight structures | 2031-04-01 | 2031-12-31 | Upcoming | RHTP team / implementing partners | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
5.3.1 | Confirm models selected for continuation | 2031-04-01 | 2031-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
5.3.2 | Complete funding, ownership, and oversight transitions | 2031-04-01 | 2031-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.

## Initiative 3 Project Plan
Initiative 3: Sustaining Rural Workforce With Training, Recruitment, and Retention |  | Key |  | Status Report
As of July 31, 2026 |  | Stage |  | 3 | Complete
Designated State Lead: | Holly Walund | Milestone |  | 10 | In Progress - On Track
Team Members: | Liz Perkins, Cecilia Arritola, Adam McFarland, Robert Graff | Task |  | 0 | In Progress - Behind Schedule
|  |  |  | 0 | Not Yet Started
|  |  |  | 73 | Upcoming
Note: All milestones from the approved State application for this initiative are included in this project plan.
Number | Milestones/Tasks | Target Start | Target Due Date | Status | Task Owner | Notes
Stage 0 | Initiation and Procurement Phase
0.1 | Finalize contracts and partnerships | 2026-05-01 | 2026-10-30 | In Progress - On Track | RHTP team | Although Idaho’s initial implementation timeline was compressed because legislative spending authority did not become effective until April 10, 2026, the State accelerated procurement, solicitation, and agreement activities following receipt of that authority and the onboarding of dedicated RHTP staff. These activities are proceeding in rolling waves across workforce incentives, career pathways, work-based learning, and GME. As of July 31, 2026, Idaho remained on track to complete the necessary awards and agreements in time to meet the October 31, 2026 obligation milestone
0.1.1 | Confirm procurement and partnership pathways for the Initiative 3 workforce components | 2026-05-01 | 2026-06-30 | Complete | RHTP team | Idaho identified the anticipated procurement, subaward, and partner-agreement pathways for workforce incentives, career pathways, work-based learning, and GME.
0.1.2 | Conduct initial coordination with State education, workforce, and healthcare partners | 2026-05-01 | 2026-07-31 | Complete | RHTP Team / Partner Agency | Initial coordination informed partner roles, scopes of work, service-commitment requirements, and implementation needs across the Initiative 3 workforce components.
0.1.3 | Develop and complete internal review of workforce solicitation and agreement packages | 2026-06-01 | 2026-09-15 | In Progress - On Track | RHTP Team | Healthcare Career Advancement, in partnership with State Board of Education solicitation and agreement packages were progressing through development and internal review as part of Idaho’s rolling procurement schedule. Application posted August 18, 2026 and will close September 17, 2026.
0.1.4 | Complete evaluations, selections, and award development | 2026-08-01 | 2026-09-30 | In Progress - On Track | RHTP Team / Partner Agency | Evaluation, selection, and award-development activities will proceed as each workforce procurement or agreement package completes the required review process.
0.1.5 | Execute workforce contracts, subawards, and partner agreements | 2026-09-01 | 2026-10-30 | In Progress - On Track | RHTP Team | Workforce contracts, subawards, and partner agreements will be executed in rolling waves and remain scheduled to support the October 31, 2026 obligation milestone.
0.2 | Develop program infrastructure, requirements, and outreach plans | 2026-11-01 | 2027-03-31 | In Progress - On Track | Partner Agency | Development of program infrastructure, requirements, and outreach plans is dependent on execution of the applicable workforce contracts and agreements. As of July 31, 2026, Idaho was procuring and formalizing the partners needed to complete this work. Program design will begin following award execution and will address eligibility, payment structures, service commitments, repayment requirements, administration, tracking, and outreach.
0.2.1 | Finalize eligibility, payment, five-year service-commitment, and repayment requirements | 2026-11-01 | 2027-01-31 | Upcoming | Partner Agency | Following agreement execution, the selected partner will translate Idaho’s approved workforce strategy into operational eligibility, payment, five-year service-commitment, and repayment requirements.
0.2.2 | Complete participant, provider, school, and community outreach plans | 2027-02-01 | 2027-03-31 | Upcoming | Partner Agency | The outreach plan will identify priority audiences, partner responsibilities, communication methods, implementation schedules, and processes for tracking engagement.
0.3 | Pilot healthcare career exploration and recruitment efforts | 2027-04-01 | 2027-09-30 | Upcoming | Partner Agency | Pilot career exploration and recruitment activities will begin after execution of the applicable agreements and completion of the initial program and outreach design under milestone 0.2. The pilot will test implementation approaches in selected rural communities before broader expansion.
0.3.1 | Select rural communities, schools, healtcare partners, and target audiences | 2027-04-01 | 2027-05-31 | Upcoming | Partner Agency | Pilot locations and partners will be selected based on rural workforce needs, community readiness, available education and healthcare partnerships, and alignment with approved program requirements
0.3.2 | Finalize pilot materials, schedules, participation processes, and tracking methods | 2027-04-01 | 2027-06-30 | Upcoming | Partner Agency | Pilot materials and processes will be finalized before launch to ensure consistent participant engagement, implementation, and performance tracking.
0.3.2 | Launch initial career exploration and targeted recruitment activities | 2027-07-01 | 2027-09-30 | Upcoming | Partner Agency | Initial activities will test Idaho’s career exploration and recruitment approach and generate participation and feedback information to inform broader implementation.
0.4 | Begin Graduate Medical Education (GME) planning and program development | 05/01826 | 2026-10-31 | In Progress - On Track | RHTP team / State education partner | As of July 31, 2026, IDHW was actively coordinating with the Idaho State Board of Education and CMS to refine Idaho’s GME strategy. Through this work, Idaho identified opportunities to expand the activities described in the original application and more fully deploy its approved GME allocation through a comprehensive statewide approach. Proposed additions include a rural GME incubator and an institution-agnostic rural clinical rotation network, which are reflected in Idaho’s BP2 Project Narrative updates. Development of the program scope, budget, deliverables, and partner agreement remained in progress. Partner-led implementation will begin after the agreement is finalized and executed.
0.4.1 | Review the original GME scope and budget to identify implementation and funding gaps | 2026-05-01 | 2026-06-30 | Complete | RHTP team / State education partner | Review of the original GME scope and budget identified the need for additional activities and a more comprehensive approach to deploying Idaho’s approved GME allocation.
0.4.2 | Coordinate with the State Board of Education and CMS to refine the proposed GME approach | 2026-06-01 | 2026-09-30 | In Progress - On Track | RHTP team / State education partner | Coordination with CMS and the State Board of Education is focused on refining the allowable scope, proposed activities, partner roles, and implementation structure.
0.4.3 | Develop the proposed rural GME incubator and clinical rotation network models | 2026-07-01 | 2026-09-30 | In Progress - On Track | RHTP team / State education partner | Idaho is developing the rural GME incubator and clinical rotation network as proposed BP2 additions to strengthen statewide GME development and rural training capacity.
0.4.4 | Finalize the GME scope, budget, deliverables, performance measures, and partner responsibilities | 2026-07-01 | 2026-10-15 | In Progress - On Track | RHTP team / State education partner | This work will translate the refined GME strategy into an agreement-ready scope, budget, set of deliverables, performance measures, and allocation of partner responsibilities.
0.4.5 | Finalize and execute the State Board of Education agreement | 2026-08-24 | 2026-10-15 | In Progress - On Track | RHTP team / State education partner | Agreement development will proceed as the GME scope, budget, proposed activities, and partner responsibilities are finalized.
0.4.6 | Conduct implementation kickoff and initiate approved GME development activities | 2026-11-01 | 2026-11-30 | Upcoming | RHTP team / State education partner | Partner-led GME implementation will begin following execution of the State Board of Education agreement and completion of the implementation kickoff.
Stage 1 | Initial Implementation Phase
1.1 | Launch preceptorships and apprenticeships | 2027-01-01 | 2027-06-30 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
1.1.1 | Execute provider and supervisor participation agreements | 2027-01-01 | 2027-06-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.1.2 | Enroll and place initial participants in rural settings | 2027-01-01 | 2027-06-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.2 | Enhance outreach and student engagement efforts | 2027-01-01 | 2027-09-30 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
1.2.1 | Expand career exploration and rural pathway outreach | 2027-01-01 | 2027-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.2.2 | Track participation and refine engagement strategies | 2027-01-01 | 2027-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.3 | Continued GME program development, instructor hiring, etc. | 2027-01-01 | 2027-12-31 | Upcoming | RHTP team / State education partner | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
1.3.1 | Advance program accreditation and site-development requirements | 2027-01-01 | 2027-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.3.2 | Recruit instructors, preceptors, and program mentors | 2027-01-01 | 2027-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.4 | Implement retention bonuses, recruitment incentives, and scholarships | 2027-01-01 | 2027-09-30 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
1.4.1 | Open applications and verify eligibility and service commitments | 2027-01-01 | 2027-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.4.2 | Issue initial approved incentive and scholarship payments | 2027-01-01 | 2027-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.5 | Launch rural residency expansions and nursing education cohorts | 2027-01-01 | 2027-09-30 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
1.5.1 | Finalize cohort, site, and instructional arrangements | 2027-01-01 | 2027-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.5.2 | Enroll and launch initial rural cohorts | 2027-01-01 | 2027-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.6 | Initiate ‘grow your own’ programs | 2027-01-01 | 2027-09-30 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
1.6.1 | Finalize participating education and community partnerships | 2027-01-01 | 2027-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.6.2 | Launch initial learn-in-place and grow-your-own pathways | 2027-01-01 | 2027-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
Stage 2 | Expansion and Integration Phase
2.1 | Fellowship and residency programs launch in rural settings | 2028-01-01 | 2028-06-30 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
2.1.1 | Complete rural site and participant onboarding | 2028-01-01 | 2028-06-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
2.1.2 | Begin rural fellowship and residency training | 2028-01-01 | 2028-06-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
2.2 | Enhanced mentorship, training, and career pathway support | 2028-01-01 | 2028-12-31 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
2.2.1 | Expand mentor, supervisor, and instructor participation | 2028-01-01 | 2028-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
2.2.2 | Deliver pathway support and monitor participant progression | 2028-01-01 | 2028-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
2.3 | Intensify recruitment incentives, retention bonuses, and scholarships | 2028-01-01 | 2028-12-31 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
2.3.1 | Expand outreach and award cycles for priority positions | 2028-01-01 | 2028-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
2.3.2 | Monitor service commitments and issue eligible payments | 2028-01-01 | 2028-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
Stage 3 | Evaluation and Refinement Phase
3.1 | Midpoint program evaluation | 2029-01-01 | 2029-06-30 | Upcoming | Evaluation vendor / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
3.1.1 | Analyze participation, placement, and retention information | 2029-01-01 | 2029-06-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
3.1.2 | Complete midpoint evaluation report | 2029-01-01 | 2029-06-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
3.2 | Adjust program design as needed | 2029-04-01 | 2029-09-30 | Upcoming | RHTP team / implementation partners | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
3.2.1 | Review evaluation findings with partners | 2029-04-01 | 2029-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
3.2.2 | Issue approved program and guidance adjustments | 2029-04-01 | 2029-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
3.3 | Enhance partnerships and training pathways | 2029-01-01 | 2029-09-30 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
3.3.1 | Identify pathway gaps and partnership opportunities | 2029-01-01 | 2029-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
3.3.2 | Expand or refine education and training pathways | 2029-01-01 | 2029-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
3.4 | Continue incentive distributions | 2029-01-01 | 2029-12-31 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
3.4.1 | Verify continued eligibility and service performance | 2029-01-01 | 2029-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
3.4.2 | Issue scheduled incentive and scholarship payments | 2029-01-01 | 2029-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
3.5 | Enhance training and career advancement | 2029-01-01 | 2029-12-31 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
3.5.1 | Assess participant advancement needs | 2029-01-01 | 2029-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
3.5.2 | Deliver enhanced training and advancement supports | 2029-01-01 | 2029-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
3.6 | Strengthen ‘grow your own’ programs | 2029-01-01 | 2029-12-31 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
3.6.1 | Review program reach and participant progression | 2029-01-01 | 2029-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
3.6.2 | Expand effective rural pathway strategies | 2029-01-01 | 2029-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
3.7 | Evaluate recruitment and retention impacts | 2029-01-01 | 2029-12-31 | Upcoming | Evaluation vendor / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
3.7.1 | Assess recruitment, vacancy, and retention trends | 2029-01-01 | 2029-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
3.7.2 | Document findings and recommendations | 2029-01-01 | 2029-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
Stage 4 | Sustainability Preparation Phase
4.1 | Continue implementation and refinement | 2030-01-01 | 2030-12-31 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
4.1.1 | Continue approved workforce program delivery | 2030-01-01 | 2030-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
4.1.2 | Implement refinements based on performance information | 2030-01-01 | 2030-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
4.2 | Plan for sustainability and post-grant transition | 2030-01-01 | 2030-12-31 | Upcoming | RHTP team / implementation partners | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
4.2.1 | Assess long-term ownership and financing options | 2030-01-01 | 2030-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
4.2.2 | Complete sustainability and transition strategy | 2030-01-01 | 2030-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
4.3 | Ongoing incentive and training delivery | 2030-01-01 | 2030-12-31 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
4.3.1 | Continue eligible incentive and scholarship payments | 2030-01-01 | 2030-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
4.3.2 | Continue training, mentorship, and career pathway support | 2030-01-01 | 2030-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
Stage 5 | Closeout and Transition Phase
5.1 | Final reporting and program closeout | 2031-01-01 | 2031-12-31 | Upcoming | RHTP team / evaluation vendor | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
5.1.1 | Complete final program and financial reporting | 2031-01-01 | 2031-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
5.1.2 | Close agreements and reconcile deliverables | 2031-01-01 | 2031-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
5.2 | Evaluate outcomes and impact | 2031-01-01 | 2031-09-30 | Upcoming | Evaluation vendor / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
5.2.1 | Complete final workforce outcome analysis | 2031-01-01 | 2031-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
5.2.2 | Document impact, limitations, and lessons learned | 2031-01-01 | 2031-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
5.3 | Disseminate findings and support transition to permanent programs | 2031-04-01 | 2031-12-31 | Upcoming | RHTP team / implementation partners | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
5.3.1 | Share results with State leaders and partners | 2031-04-01 | 2031-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
5.3.2 | Transition continuing programs to long-term owners | 2031-04-01 | 2031-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.

## Initiative 4 Project Plan
Initiative 4: Implementing Population-Specific, Evidence-Based Projects to Make America Healthy Again |  | Key |  | Status Report
As of July 31, 2026 |  | Stage |  | 2 | Complete
Designated State Lead: | Holly Walund | Milestone |  | 17 | In Progress - On Track
Team Members: | Liz Perkins, Cecilia Arritola, Adam McFarland, Robert Graff | Task |  | 0 | In Progress - Behind Schedule
|  |  |  | 0 | Not Yet Started
|  |  |  | 51 | Upcoming
Note: All milestones from the approved State application for this initiative are included in this project plan.
Number | Milestones/Tasks | Target Start | Target Due Date | Status | Task Owner | Notes
Stage 0 | Initiation and Procurement Phase
0.1 | Contract award and kickoff | 2026-05-01 | 2026-10-30 | In Progress - On Track | RHTP and grants/contracts teams | Initiative 4 procurement and award activities are proceeding in rolling waves. Idaho completed the competitive solicitation and selection processes for the Obstetric Readiness and Idaho Perinatal Quality Collaborative projects and issued award letters to Comagine Health on July 30, 2026. Agreement finalization, kickoff, and implementation planning for these projects are advancing while Idaho concurrently completes procurement and award activities for the remaining Initiative 4 programs. Idaho remains on track to complete the necessary awards and agreements in support of the October 31, 2026 obligation milestone.
0.1.1 | Complete the competitive solicitation, evaluation, and selection processes for the MCH projects | 2026-06-05 | 2026-07-29 | Complete | RHTP Team | Idaho completed the competitive solicitation, evaluation, and selection processes for the Obstetric Readiness and Idaho Perinatal Quality Collaborative projects, resulting in the selection of Comagine Health for both awards
0.1.2 | Issue award letters for Obstetric Readiness and the Idaho Perinatal Quality Collaborative | 2026-07-30 | 2026-07-30 | Complete | RHTP Team | IDHW issued award letters to Comagine Health on July 30, 2026, formally communicating its selection for the Obstetric Readiness and Idaho Perinatal Quality Collaborative projects.
0.1.3 | Finalize MCH agreements, approved workplans, budgets, and implementation requirements | 2026-07-30 | 2026-10-12 | In Progress - On Track | RHTP and grants/contracts teams | Following award notification, IDHW and Comagine Health began finalizing the agreements, approved workplans, budgets, deliverables, and implementation requirements for both MCH projects.
0.1.4 | Conduct MCH implementation kickoff and confirm initial deliverables and reporting expectations | 2026-09-01 | 2026-09-15 | In Progress - On Track | RHTP and selected vendor | The MCH kickoff process will confirm project governance, initial deliverables, reporting expectations, implementation schedules, and coordination responsibilities for the two awarded projects.
0.1.5 | Advance remaining Initiative 4 solicitations through evaluation, selection, and award development | 2026-06-01 | 2026-10-15 | In Progress - On Track | RHTP Team | Idaho has released additional Initiative 4 funding opportunities and is advancing them through the rolling solicitation, application, evaluation, and award-development process. Each opportunity will proceed to selection and agreement execution as its respective procurement cycle is completed.
0.1.6 | Execute remaining Initiative 4 contracts and subawards | 2026-09-01 | 2026-10-30 | In Progress - On Track | RHTP and grants/contracts teams | Agreement templates, award requirements, and execution processes are being prepared concurrently with the remaining solicitation and evaluation activities. Agreements will be finalized in rolling waves following selection and remain scheduled to support the October 30 obligation milestone
0.2 | Establish partnerships | 2026-07-30 | 2026-12-31 | In Progress - On Track | RHTP team / implementation partners | Partnership development is underway in rolling waves. Following the July 30 MCH award notifications, IDHW and Comagine Health began formalizing roles, workplans, implementation expectations, and coordination with participating rural hospitals and other MCH stakeholders. Partnerships supporting the remaining chronic disease and behavioral health activities will be formalized as those procurements and awards are completed.
0.2.1 | Confirm IDHW and Comagine Health roles and coordination processes. | 2026-08-01 | 2026-12-31 | In Progress - On Track | Implementing partners / RHTP team | Idaho RHTP and Comagine Health are formalizing roles, communication processes, decision-making responsibilities, and coordination expectations for the two awarded MCH projects.
0.2.2 | Establish the participation and communication approach for rural hospitals and MCH stakeholders. | 2026-08-01 | 2026-12-31 | In Progress - On Track | Implementing partners / RHTP team | The participation and communication approach will define how rural hospitals, clinical partners, and other MCH stakeholders engage in the Obstetric Readiness and Idaho Perinatal Quality Collaborative projects.
0.2.3 | Formalize partnerships for remaining Initiative 4 programs following award selection. | 2026-05-01 | 2026-12-31 | In Progress - On Track | Implementing partners / RHTP team | Partnerships for the remaining chronic disease and behavioral health programs will be formalized as each funding opportunity completes evaluation, selection, and agreement execution.
0.3 | Finalize program protocols | 2026-08-01 | 2027-03-31 | In Progress - On Track | Implementation partners / RHTP team | Program-protocol development has begun for the awarded MCH projects and will continue through agreement finalization and implementation planning. IDHW and Comagine Health will refine the Obstetric Readiness and Idaho Perinatal Quality Collaborative protocols, participation requirements, deliverables, and quality expectations. Protocols for the remaining Initiative 4 programs will be finalized following execution of the applicable awards and agreements.
0.3.1 | Review and finalize the Obstetric Readiness implementation protocols. | 2026-07-01 | 2026-12-31 | In Progress - On Track | Implementing partners / RHTP team | Review the proposed Obstetric Readiness approach to finalize participating-hospital requirements, implementation activities, deliverables, quality expectations, and reporting responsibilities.
0.3.2 | Review and finalize the Idaho Perinatal Quality Collaborative operating and participation protocols. | 2026-07-01 | 2026-12-31 | In Progress - On Track | Implementing partners / RHTP team | Refine the Idaho Perinatal Quality Collaborative operating model, hospital-participation expectations, collaborative activities, deliverables, and performance requirements.
0.3.3 | Finalize protocols for remaining Initiative 4 programs after award execution | 2026-11-01 | 2027-03-31 | In Progress - On Track | Implementing partners / RHTP team | Program protocols for the remaining Initiative 4 activities will be developed and finalized with the selected implementation partners following execution of the applicable agreements.
0.4 | Develop data systems | 2026-07-01 | 2026-12-31 | In Progress - On Track | Evaluation vendor / RHTP team | Initial development of Initiative 4 data and reporting requirements is underway, including identification of MCH performance measures, participating-entity reporting expectations, and data needed to monitor implementation and outcomes. IDHW is also finalizing a cooperative agreement with a data analytics and outcomes evaluation vendor that will help lead and coordinate data collection, validation, analysis, and performance reporting across Initiative 4 and the broader RHTP. Requirements will be incorporated into applicable agreements, workplans, and the statewide evaluation approach, with operational data-collection processes implemented as individual programs launch.
0.4.1 | Define measures, data sources, and reporting responsibilities | 2026-07-01 | 2026-12-31 | In Progress - On Track | RHTP team/ Implementation partners | Idaho RHTP and its implementation partners are identifying program-specific measures, data sources, reporting frequency, responsible parties, and information needed to monitor implementation and outcomes
0.4.2 | Finalize and execute the data analytics and outcomes evaluation cooperative agreement | 2026-07-13 | 2026-10-30 | In Progress - On Track | RHTP Team and grants and contracts teams | Idaho RHTP is actively finalizing a cooperative agreement with a data analytics and outcomes evaluation vendor. Following execution, the vendor will help lead and coordinate data collection, validation, analysis, outcome measurement, and performance reporting across Initiative 4 and the broader RHTP.
0.4.2 | Establish collection, validation, and submission processes | 2026-08-01 | 2026-12-31 | In Progress - On Track | Implementing partners / RHTP team /Evaluation vendor | Idaho RHTP is developing the foundational reporting approach while the cooperative agreement is finalized. The evaluation vendor will help refine and operationalize processes for participating entities to submit data, validate completeness and accuracy, analyze results, and incorporate findings into RHTP performance reporting.
0.5 | Launch initial programs (NDPP, Pediatric Psychiatry Access Line) | 2026-11-01 | 2027-03-31 | Upcoming | Implementation partners | Launch of the initial chronic disease and behavioral health programs is dependent on completion of the applicable solicitation, selection, and agreement execution processes. Procurement activities are currently underway, and implementation will begin following execution of the applicable awards and agreements.
0.5.1 | Complete program readiness and participant outreach | 2026-07-01 | 2026-12-31 | Upcoming | Implementing partners / RHTP team | Following agreement execution, selected partners will complete program-readiness activities, establish referral and enrollment processes, prepare outreach materials, and confirm participating sites and populations
0.5.2 | Begin service delivery and participation tracking | 2026-07-01 | 2026-12-31 | Upcoming | Implementing partners / RHTP team | Service delivery and participant tracking will begin after completion of program-readiness activities and approval of the applicable implementation and data-collection processes.
0.6 | Start training and certification programs | 2026-11-01 | 2027-06-30 | Upcoming | Implementation partners | Training and certification activities are dependent on selection and agreement execution for the applicable Initiative 4 programs. Selected implementation partners will finalize training requirements and schedules after award execution, with delivery beginning as individual programs become operational.
0.6.1 | Finalize training curriculum, schedule, and participant criteria | 2026-11-01 | 2027-03-31 | Upcoming | Implementing partners / RHTP team | Selected partners will finalize the curriculum, delivery format, training schedule, participant eligibility requirements, and processes for documenting attendance, successful completion, and certification, where applicable.
0.6.2 | Deliver initial training and document completion | 2027-02-01 | 2027-06-30 | Upcoming | Implementing partners / RHTP team | Initial training will be delivered as the applicable programs become operational, and participant attendance, completion, and certification information will be documented for performance reporting.
Stage 1 | Initial Implementation Phase
1.1 | Scale chronic disease and mental health programs | 2027-01-01 | 2027-12-31 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
1.1.1 | Expand participating sites and participant outreach | 2027-01-01 | 2027-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.1.2 | Monitor delivery, enrollment, retention, and quality | 2027-01-01 | 2027-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.2 | Collect baseline data | 2027-01-01 | 2027-12-31 | Upcoming | Evaluation vendor / implementation partners | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
1.2.1 | Collect and validate program baseline information | 2027-01-01 | 2027-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.2.2 | Complete first initiative data reports | 2027-01-01 | 2027-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
Stage 2 | Expansion and Midpoint Evaluation Phase
2.1 | Conduct mid-project evaluation | 2028-01-01 | 2028-06-30 | Upcoming | Evaluation vendor / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
2.1.1 | Analyze implementation and outcome information | 2028-01-01 | 2028-06-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
2.1.2 | Complete midpoint evaluation report | 2028-01-01 | 2028-06-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
2.2 | Adjust program strategies | 2028-04-01 | 2028-09-30 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
2.2.1 | Review findings with program partners | 2028-04-01 | 2028-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
2.2.2 | Implement approved program modifications | 2028-04-01 | 2028-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
2.3 | Deepen community engagement | 2028-01-01 | 2028-12-31 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
2.3.1 | Gather participant and community feedback | 2028-01-01 | 2028-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
2.3.2 | Strengthen outreach and community partnerships | 2028-01-01 | 2028-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
2.4 | Enhance prevention programs | 2028-01-01 | 2028-12-31 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
2.4.1 | Identify effective practices and remaining gaps | 2028-01-01 | 2028-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
2.4.2 | Expand or refine prevention services | 2028-01-01 | 2028-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
Stage 3 | Evaluation and Sustainability Phase
3.1 | Develop sustainability plans | 2029-01-01 | 2029-06-30 | Upcoming | RHTP team / implementation partners | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
3.1.1 | Assess long-term financing and ownership options | 2029-01-01 | 2029-06-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
3.1.2 | Complete program-specific sustainability plans | 2029-01-01 | 2029-06-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
3.2 | Enhance data-driven decision making | 2029-01-01 | 2029-12-31 | Upcoming | Evaluation vendor / implementation partners | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
3.2.1 | Provide routine performance reporting to program teams | 2029-01-01 | 2029-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
3.2.2 | Use findings to guide improvement decisions | 2029-01-01 | 2029-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
Stage 4 | Completion and Transition Phase
4.1 | Complete program delivery | 2030-01-01 | 2030-12-31 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
4.1.1 | Complete planned service-delivery activities | 2030-01-01 | 2030-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
4.1.2 | Verify participant and deliverable records | 2030-01-01 | 2030-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
4.2 | Conduct long-term outcome evaluation | 2030-01-01 | 2030-06-30 | Upcoming | Evaluation vendor / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
4.2.1 | Analyze longer-term program outcomes | 2030-01-01 | 2030-06-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
4.2.2 | Complete outcome evaluation findings | 2030-01-01 | 2030-06-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
4.3 | Prepare final reports | 2030-04-01 | 2030-12-31 | Upcoming | RHTP team / evaluation vendor | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
4.3.1 | Compile final narrative and metric results | 2030-04-01 | 2030-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
4.3.2 | Prepare required final reports | 2030-04-01 | 2030-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
4.4 | Transition ownership to local/state entities | 2030-04-01 | 2030-12-31 | Upcoming | RHTP team / implementation partners | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
4.4.1 | Confirm continuing program owners | 2030-04-01 | 2030-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
4.4.2 | Complete operational and data transitions | 2030-04-01 | 2030-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
Stage 5 | Closeout and Dissemination Phase
5.1 | Complete administrative closeout | 2031-01-01 | 2031-06-30 | Upcoming | RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
5.1.1 | Close agreements and reconcile deliverables | 2031-01-01 | 2031-06-30 | Upcoming | RHTP team | Planned task supporting the approved milestone.
5.1.2 | Complete closeout documentation | 2031-01-01 | 2031-06-30 | Upcoming | RHTP team | Planned task supporting the approved milestone.
5.2 | Public dissemination of outcomes | 2031-04-01 | 2031-09-30 | Upcoming | RHTP team / evaluation vendor | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
5.2.1 | Prepare stakeholder-facing findings | 2031-04-01 | 2031-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
5.2.2 | Conduct public and partner briefings | 2031-04-01 | 2031-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
5.3 | Document lessons learned | 2031-04-01 | 2031-12-31 | Upcoming | RHTP team / evaluation vendor | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
5.3.1 | Gather final implementation lessons | 2031-04-01 | 2031-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
5.3.2 | Complete knowledge-dissemination products | 2031-04-01 | 2031-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
Note on G16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Walund, Holly - CO 4th can we add anticipated closing and award dates here too as we have for other initiatives? And any other anticipated dates for activities in the notes below.

## Initiative 5 Project Plan
Initiative 5: Investing in Rural Health Infrastructure and Partnerships |  | Key |  | Status Report
As of July 31, 2026 |  | Stage |  | 9 | Complete
Designated State Lead: | Holly Walund | Milestone |  | 10 | In Progress - On Track
Team Members: | Liz Perkins, Cecilia Arritola, Adam McFarland, Robert Graff | Task |  | 0 | In Progress - Behind Schedule
|  |  |  | 0 | Not Yet Started
|  |  |  | 50 | Upcoming
Note: All milestones from the approved State application for this initiative are included in this project plan.
Number | Milestones/Tasks | Target Start | Target Due Date | Status | Task Owner | Notes
Stage 0 | Initiation and Procurement Phase
0.1 | Execute contracts and engage healthcare facility and partner stakeholders | 2026-05-01 | 2026-10-30 | In Progress - On Track | RHTP team and grants/contracts team | Initiative 5 procurement, subaward, and partnership activities are proceeding in rolling waves. IDHW completed its review and selection process for the five noncompetitive Tribal subawards and issued award notification letters to each of Idaho’s five federally recognized Tribes on July 30, 2026. The Tribal subaward agreements are currently being finalized and executed. IDHW has also advanced the competitive Healthcare Infrastructure Support opportunity and associated stakeholder engagement activities. Idaho remains on track to execute the necessary Initiative 5 agreements in support of the October 31, 2026 obligation milestone.
0.1.1 | Confirm procurement and subaward pathways for Initiative 5 investments | 2026-05-01 | 2026-08-18 | Complete | RHTP team | Idaho RHTP confirmed the noncompetitive subaward pathway for Tribal investments and the competitive subaward approach for broader healthcare infrastructure investments.
0.1.2 | Complete review of the five noncompetitive Tribal subaward proposals | 2026-05-01 | 2026-07-30 | Complete | RHTP team | Idaho RHTP completed its review of the plans and proposed activities submitted by Idaho’s five federally recognized Tribes and confirmed alignment with Idaho’s approved RHTP strategy.
0.1.3 | Issue Tribal subaward notification letters | 2026-07-30 | 2026-07-30 | Complete | RHTP team | IDHW issued award notification letters to each of Idaho’s five federally recognized Tribes on July 30, 2026.
0.1.4 | Finalize and execute the five Tribal subaward agreements | 2026-08-01 | 2026-10-30 | In Progress - On Track | RHTP team | Idaho RHTP and the five Tribal awardees are finalizing subaward agreements, approved workplans, budgets, reporting requirements, and implementation expectations. The agreements remain in execution as of the current project plan update.
0.1.5 | Release and administer the Healthcare Infrastructure Support solicitation | 0818/26 | 2026-10-18 | In Progress - On Track | RHTP team | The Healthcare Infrastructure Support opportunity is advancing through Idaho’s competitive subaward process, including applicant engagement, informational activities, solicitation administration, and preparation for evaluation and award development.
0.1.6 | Complete evaluation, selection, award development, and agreement execution for remaining Initiative 5 investments | 2026-10-18 | 2026-10-30 | In Progress - On Track | RHTP and grants/contracts teams | Remaining Initiative 5 awards and agreements will proceed in rolling waves as the applicable application, evaluation, selection, and pre-award review activities are completed.
0.2 | Begin facility and infrastructure needs assessments | 2026-05-01 | 2026-10-18 | In Progress - On Track | RHTP team / assessment partners | Facility and infrastructure needs assessment activities are underway through review of existing rural healthcare information, stakeholder input, and the Healthcare Infrastructure Support application process. The solicitation requires applicants to document identified facility, equipment, vehicle, technology, pharmacy, safety, and other infrastructure needs. IDHW will use application information, supporting documentation, and post-selection workplans to validate and prioritize proposed investments.
0.2.1 | Compile available facility assessments, stakeholder input, and rural infrastructure needs information | 2026-05-01 | 2026-12-31 | Complete | Implementing partners / RHTP team | Idaho RHTP reviewed available rural healthcare information, stakeholder feedback, and identified infrastructure needs to inform development of the Healthcare Infrsastructure Support (HIS) opportunity.
0.2.2 | Translate identified needs into eligible HIS investment categories and application requirements | 2026-05-01 | 2026-08-18 | Complete | Implementing partners / RHTP team | Identified needs were translated into eligible HIS investment categories and application requirements covering facility renovatoins, equipment, vehicles, tehcnology, pharmacy, safety, and other rural healthcare infrastructure.
0.2.3 | Collect facility-specific needs information and supporting documentation through applications | 2026-08-18 | 2026-10-18 | In Progress - On Track | Implementing partners / RHTP team | The HIS application process is collecting facility-specific information regarding identified needs, proposed investments, anticipated benefits, project readiness, budgets and supporting documentation.
0.2.4 | Validate selected infrastructure needs through pre-award review and detailed workplans | 2026-10-13 | 2026-12-31 | Upcoming | Implementing partners / RHTP team | Following application evaluation and preliminary selection, Idaho RHTP will validate proposed infrastructure needs, costs, readiness, and implementation requirements through pre-award review and detailed workplan development.
0.3 | Develop application and prioritization process for renovations, equipment, and vehicle requests | 2026-05-01 | 2026-09-30 | In Progress - On Track | RHTP team | IDHW completed and launched the Healthcare Infrastructure Support application process, including eligible investment categories, application requirements, and scored evaluation criteria. The remaining component of this milestone is establishment of a documented approach for prioritizing and allocating funds among eligible, highly scored proposals when requests exceed available resources or require portfolio-level funding decisions. This work remains under consideration and should be resolved before evaluation and award recommendations are finalized to support consistent, transparent, and defensible funding decisions.
0.3.1 | Define eligible infrastructure categories and application requirements | 2026-05-01 | 2026-09-30 | Complete | RHTP team | Eligible renovation, equipment, vehicle, and related infrastructure categories and application requirements were incorporated into the HIS opportunity.
0.3.2 | Develop and publish scored application-evaluation criteria | 2026-05-01 | 2026-08-18 | Complete | RHTP Team | Scored criteria were established and published as part of the HIS opportunity.
0.3.3 | Finalize and release the HIS funding opportunity | 2026-05-01 | 2026-08-18 | Complete | RHTP Team | The HIS funding opportunity was finalized and released to eligible applicants on August 18, 2026.
0.3.4 | Finalize and document the HIS prioritization and funding-allocation approach | 2026-08-01 | 2026-09-15 | In Progress - On Track | RHTP and grants/contracts teams | Idaho RHTP is finalizing the approach for prioritizing eligible proposals and allocating available funding. The approach will be reviewed and documented before award recommendations are finalized to support consistent and defensible funding decisions.
0.4 | Work with five federally recognized Native nations in Idaho to submit a coordinated proposal for use of the three and a half percent set-aside over the five-year period | 2026-05-01 | 2026-12-31 | In Progress - On Track | RHTP team / Tribes of Idaho | Idaho RHTP worked with Idaho’s five federally recognized Tribes to review proposed uses of the Tribal set-aside and issued noncompetitive subgrant award notifications to all five Tribes on July 30, 2026. Subgrant agreements are now being finalized and executed, with individual kickoff meetings planned as agreements are completed
0.4.1 | Complete review and acceptance of Tribal plans and issue award notifications | 2026-05-01 | 2026-07-30 | Complete | RHTP Team | Proposed Tribal activities were reviewed for alignment with RHTP requirements, and award notifications were issued to all five Tribes on July 30, 2026.
0.4.2 | Execute final Tribal subgrant agreements | 2026-07-30 | 2026-10-30 | In Progress - On Track | RHTP and grants/contracts teams | Award notifications were issued to all five federally recognized Tribes on July 30, 2026. Idaho RHTP and its grants and contracts teams are working with each Tribe to finalize and execute subgrant agreements incorporating the approved scope, budget, reporting requirements, and implementation expectations.
0.4.3 | Host subgrant kick-off with each of the five federally recognized Native nations in Idaho to clarify workplans, review invoicing procedures and kick-off projects. | 2026-09-01 | 2026-11-30 | Upcoming | RHTP and grants/contracts teams | Idaho RHTP will host individual subgrant kickoff meetings, which will occur as agreements are executed. Each kickoff will confirm the approved workplan and implementation schedule, review invoicing, and reporting procedures, clarify roles and expectations, and support timely project launch.
Stage 1 | Initial Infrastructure Implementation Phase
1.1 | Begin disbursing funds for renovations | 2027-01-01 | 2027-12-31 | Upcoming | Subrecipients / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
1.1.1 | Approve project workplans, budgets, and required prior approvals | 2027-01-01 | 2027-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.1.2 | Begin renovation work and reimbursement monitoring | 2027-01-01 | 2027-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.2 | Launch pharmacy facility upgrades and clinical pharmacy integration projects | 2027-01-01 | 2027-12-31 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
1.2.1 | Finalize participating sites and implementation plans | 2027-01-01 | 2027-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.2.2 | Begin pharmacy upgrades and clinical integration work | 2027-01-01 | 2027-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.3 | Initiate purchase of clinical equipment and safety code compliance grants | 2027-01-01 | 2027-12-31 | Upcoming | Subrecipients / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
1.3.1 | Review proposed purchases and applicable approval requirements | 2027-01-01 | 2027-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.3.2 | Authorize purchases and monitor receipt and asset documentation | 2027-01-01 | 2027-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.4 | Develop GME and health extender training space renovation plans | 2027-01-01 | 2027-12-31 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
1.4.1 | Confirm space, program, and facility requirements | 2027-01-01 | 2027-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.4.2 | Complete renovation designs and implementation schedules | 2027-01-01 | 2027-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.5 | Deploy mobile health units and patient transport vehicles | 2027-01-01 | 2027-06-30 | Upcoming | Subrecipients / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
1.5.1 | Approve vehicle specifications, service areas, and operating plans | 2027-01-01 | 2027-06-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
1.5.2 | Acquire and deploy mobile units and transport vehicles | 2027-01-01 | 2027-06-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
Stage 2 | Expansion and Utilization Phase
2.1 | Implement and evaluate upgraded training and telehealth spaces | 2028-01-01 | 2028-09-30 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
2.1.1 | Complete renovations and operational readiness checks | 2028-01-01 | 2028-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
2.1.2 | Begin use and evaluate utilization and functionality | 2028-01-01 | 2028-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
2.2 | Continue supporting pharmacy access and chronic disease program space renovations | 2028-01-01 | 2028-12-31 | Upcoming | Implementing partners / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
2.2.1 | Monitor construction, installation, and implementation progress | 2028-01-01 | 2028-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
2.2.2 | Verify completion and expanded service capacity | 2028-01-01 | 2028-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
Stage 3 | Monitoring and Technical Assistance Phase
3.1 | Monitor implementation progress and gather facility-level impact data | 2029-01-01 | 2029-12-31 | Upcoming | RHTP team / evaluation vendor | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
3.1.1 | Review progress, expenditure, and asset information | 2029-01-01 | 2029-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
3.1.2 | Collect facility-level access, capacity, and utilization data | 2029-01-01 | 2029-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
3.2 | Provide technical assistance for sustained maintenance of infrastructure and equipment | 2029-01-01 | 2029-09-30 | Upcoming | RHTP team / technical assistance partners | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
3.2.1 | Assess maintenance and operational support needs | 2029-01-01 | 2029-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
3.2.2 | Deliver technical assistance and corrective-action support | 2029-01-01 | 2029-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
3.3 | Continue partnership development | 2029-01-01 | 2029-12-31 | Upcoming | RHTP team / implementation partners | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
3.3.1 | Identify collaboration and shared-use opportunities | 2029-01-01 | 2029-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
3.3.2 | Formalize partnerships supporting sustained access | 2029-01-01 | 2029-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
Stage 4 | Optimization and Sustainability Phase
4.1 | Optimize infrastructure and equipment utilization across facilities | 2030-01-01 | 2030-09-30 | Upcoming | Subrecipients / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
4.1.1 | Review utilization and remaining capacity gaps | 2030-01-01 | 2030-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
4.1.2 | Implement approved optimization strategies | 2030-01-01 | 2030-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
4.2 | Identify lessons learned and best practices | 2030-01-01 | 2030-09-30 | Upcoming | Evaluation vendor / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
4.2.1 | Gather implementation experience from participating entities | 2030-01-01 | 2030-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
4.2.2 | Document transferable practices and lessons | 2030-01-01 | 2030-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
4.3 | Support long-term planning for sustainability and facility maintenance post-grant | 2030-01-01 | 2030-12-31 | Upcoming | RHTP team / subrecipients | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
4.3.1 | Estimate long-term operating and maintenance requirements | 2030-01-01 | 2030-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
4.3.2 | Complete sustainability and maintenance plans | 2030-01-01 | 2030-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
Stage 5 | Closeout and Transition Phase
5.1 | Conduct final evaluation of infrastructure investments and partnerships | 2031-01-01 | 2031-06-30 | Upcoming | Evaluation vendor / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
5.1.1 | Compile final project and outcome information | 2031-01-01 | 2031-06-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
5.1.2 | Complete final evaluation and impact report | 2031-01-01 | 2031-06-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
5.2 | Complete reporting on access, service expansion, and safety improvements | 2031-01-01 | 2031-09-30 | Upcoming | Evaluation vendor / RHTP team | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
5.2.1 | Analyze access, capacity, service, and safety results | 2031-01-01 | 2031-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
5.2.2 | Complete required final reporting | 2031-01-01 | 2031-09-30 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
5.3 | Disseminate outcomes and recommendations for future rural health infrastructure planning | 2031-04-01 | 2031-12-31 | Upcoming | RHTP team / evaluation vendor | Planned milestone from the approved project narrative; timing and deliverables will be refined through implementation planning.
5.3.1 | Share results with policymakers and stakeholders | 2031-04-01 | 2031-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.
5.3.2 | Publish recommendations for future infrastructure planning | 2031-04-01 | 2031-12-31 | Upcoming | Implementing partners / RHTP team | Planned task supporting the approved milestone.